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Hoi An, 19 July 2023


Decision 

On adjustment of the plan to hold the architectural design competition
for Kim Bong bridge (Cam Kim local bridge), Hoi An City

PEOPLE’S COMMITTEE OF HOI AN CITY

Pursuant to the Law on Government Organization dated 19 June 2015; the Law amending and supplementing a number of articles of the Law on Government Organization and the Law on Local Government Organization dated 22 November 2019;

Pursuant to the Law on Urban Planning No. 30/2009/QH12 dated 17 June 2009;

Pursuant to the Construction Law No. 50/2014/QH13 dated 18 June 2014; the Law No. 62/2020/QH14 dated 17 June 2020 amending and supplementing a number of articles of the Construction Law;

Pursuant to the Law No. 35/2018/QH14 dated 20 November 2018 amending and supplementing a number of articles concerning planning of 37 laws;
Pursuant to the Law on Architecture No. 40/2019/QH14 dated 13 June 2019;

Pursuant to Government’s Decree No. 85/2020/ND-CP dated 17 July 2020 detailing a number of articles of the Law on Architecture;

Pursuant to Decision No. 744/QD-UBND dated 07 June 2022 by the People’s Committee of Hoi An City approving the plan to hold an architectural design competition for Kim Bong bridge (Cam Kim local bridge);

At the request of the Urban Management Department as per Report No. 261/TTr-QLDT dated 13 July 2023 on the proposal to consider and approve the adjustment of the plan to hold the architectural design competition for Kim Bong bridge (Cam Kim local bridge), Hoi An City;
Decides:

Article 1. Approve the adjustment of Clause IV, Article 1 of Decision No. 744/QD-UBND dated 07 June 2022 by the People’s Committee of Hoi An City approving the plan to hold the architectural design competition for Kim Bong bridge (Cam Kim local bridge) as follows:
	No.
	CONTENT
	EXECUTION TIME

	I
	PREPARATION

	1
	Collect documents, data; synthesize and complete legal documents related to the competition
	05 days
	14 Apr 2023 – 18 Apr 2023

	2
	- Develop the content of regulations, tasks, and program for competition

- Develop regulations for the Jury Board
	15 days
	14 Apr 2023 – 18 Apr 2023

	3
	Prepare budget estimates and submit budget estimates for approval
	10 days
	19 Apr 2023 – 28 Apr 2023

	4
	Send invitations to join the Jury Board
	10 days
	29 Apr 2023 – 08 May 2023

	5
	Establish the Jury Board and the Technical Team
	07 days
	09 May 2023 – 15 May 2023

	6
	Receive feedback on the draft regulations and tasks
	25 days
	16 May 2023 – 09 Jun 2023

	7
	Complete documents on regulations, tasks, and program
	20 days
	10 May 2023 – 28 Jun 2023

	8
	Approve regulations, tasks, and program for the competition
	15 days
	29 Jun 2023 – 13 Jul 2023

	II
	COMPETITION

	9
	- Set up and launch a website for the competition

- Announce the information about the competition and invite participants

- Receive submissions
	12 days
	14 Jul 2023 – 25 Jul 2023

	10
	Preliminary review and invite competitors
	03 days
	26 Jul 2023 – 28 Jul 2023

	11
	Survey the current status of the site
	02 days
	29 Jul 2023 – 30 Jul 2023

	12
	Competitors proceed with their designs
	45 days
	31 Jul 2023 – 13 Sep 2023

	13
	Receive the entries
	01 day
	14 Sep 2023

	14
	Review the entries
	07 days
	15 Sep 2023 – 21 Sep 2023

	15
	Exhibition of the entries (expected place at the People’s Committee of Hoi An City)
	07 days
	18 Sep 2023 – 24 Sep 2023

	16
	Competitors defend their designs
	15 days
	25 Sep 2023 – 09 Oct 2023

	17
	The Jury Board evaluates the entries
	
	

	III
	RESULT ANNOUNCEMENT AND AWARDS

	18
	Decision to recognize the results
	15 days
	10 Oct 2023 – 24 Oct 2023

	19
	Announcement and awards
	
	October 2023


Article 2. This Decision amends and supplements Decision No. 744/QD-UBND dated 07 June 2022 by the People’s Committee of Hoi An City.
Article 3. Chief of Office of the People’s Committee, Head of the Urban Management Department, Heads of relevant departments and divisions are responsible for implementing this Decision./.
	Recipients:

· City Party Committee;
· Vice Chairmen of the City People’s Committee;
· City People’s Council;
· 02 City Council Committees;

· As in Article 3;

· Archive: VT-UBND (HL).

	ON BEHALF OF THE PEOPLE’S COMMITTEE OF HOI AN CITY
CHAIRMAN
 (signed and sealed)

NGUYEN VAN SON


